## Staffing Plan
Ramp pattern follows the Acme SD phase closely for design-heavy roles; Site Observation staffing starts two weeks into Construction Management, once the contractor mobilizes on site.
Phase / Task / Resource | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
01 Schematic Design
Project Architect | 32 | 40 | 40 | 38 | 35 | 30 | 20 | 0 | 0 | 0 | 0 | 0
02 Construction Management
02.01 Contract Administration
Project Architect | 16 | 16 | 20 | 20 | 20 | 18 | 18 | 16 | 16 | 12 | 12 | 8
02.02 Site Observation
Field Observer | 0 | 0 | 0 | 8 | 12 | 16 | 16 | 16 | 12 | 12 | 8 | 4