## Staffing Plan
This staffing plan is based on the Riverside Medical Center project pattern. The work follows a typical healthcare facility delivery with an early Schematic Design phase (weeks 1–2) led by the Project Architect with designer support ramping in week 2, followed by Construction Management activities (weeks 3–6). The Project Architect maintains continuous involvement throughout, with peak effort in early design and contract administration, then tapering during site observation. Field Observer effort ramps up steadily during construction to support inspections and site walks.
Phase / Task / Resource | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
01 Schematic Design
01.SD Schematic Design
Project Architect | 48 | 32 | 0 | 0 | 0 | 0
Designer I | 0 | 12 | 0 | 0 | 0 | 0
02 Construction Management
02.CA Contract Administration
Project Architect | 0 | 0 | 0 | 32 | 16 | 0
02.SO Site Observation
Field Observer | 0 | 0 | 0 | 8 | 12 | 12